# Leadership Supervision and Programme Management practice worksheet

SWP-033 | Version 1.1.0 | SWEEP Academy

Apply all three lessons to the fictional case below. Do not use identifiable service-user information. Write a reasoned plan that makes uncertainty and decision authority explicit.

Use the laws, professional scope, organisational policies and approved referral routes that apply to your setting. This course is educational and does not replace urgent safeguarding, clinical or legal procedures. All worked cases are fictional. Research notes distinguish published findings from SWEEP teaching examples.

# Practice case

A community programme is expanding its outreach sessions. Two teams share staff, a manager has a personal connection to a potential supplier, and delayed referrals are adding pressure. The board wants more sessions, while workers report that preparation and follow-up time are insufficient.

## Activity 1

Write a short delegation note for the outreach coordinator. Include one permitted decision, one limit, a support contact and an escalation route.

Write your response here

## Activity 2

Prepare a supervision agenda for the outreach case with a reflection question, a specific feedback observation, an agreed action and an urgent-issue route.

Write your response here

## Activity 3

Write an issue log entry and a change proposal for the outreach programme. Give one output measure and one outcome-oriented measure.

Write your response here

# Self assessment and facilitator discussion

For each activity, use 0 for missing reasoning, 1 for a partly justified response and 2 for a justified response with relevant safeguards and limits. This is a formative rubric, not the platform's certification score.

## Activity 1 criteria

Authority is explicit and bounded. The response separates management authority from specialist competence and describes a transparent conflict-of-interest process.

## Activity 2 criteria

The agenda balances learning and support with accountability, tests assumptions, addresses work design and does not postpone urgent concerns until the next meeting.

## Activity 3 criteria

The entry explains impact and ownership. The proposal investigates causes, stays within authority and defines how service effects will be reviewed.

## Next learning step

Identify one assumption you changed and one procedure you must verify locally. Explain who can resolve it before you apply the plan in practice.

# Sources and evidence limits

[R3] Viscu, L.-I., and Marici, M. (2024). Challenges in supervising social workers. International Journal of Social and Educational Innovation, 11(22), 81-94. https://zenodo.org/records/14246369

[S2] NASW and ASWB. Best Practice Standards in Social Work Supervision. https://www.socialworkers.org/Practice/NASW-Practice-Standards-Guidelines/Best-Practice-Standards-in-Social-Work-Supervision

[S4] IFSW (2018). Global Social Work Statement of Ethical Principles. https://www.ifsw.org/global-social-work-statement-of-ethical-principles/

The index record is a discovery aid, not a guarantee of quality. Read the source before applying its findings to a different setting. No article endorses this course.